## Start here
MH-USA ¦ Pallet Rack Quote Comparison
Compare three quotes against the same project brief—not just the lowest headline price.
(800) 326-4403 | sales@mh-usa.com | mh-usa.com
Step / rule | Instructions
1 · Define one project | Complete Project brief. Send the same revision, load information and quantities to each supplier.
2 · Copy each quote | In Quote A / B / C, enter supplier, reference, currency and the quoted total exactly as supplied.
3 · Classify every scope line | Included = inside the quoted total, even if itemized separately. Extra cost = outside it. By others = outside it and supplied by another party. Not needed requires agreement. Unclear stays unresolved.
4 · Add only missing costs | For Extra cost / By others, enter a nonnegative amount outside the quoted total. A verified zero is allowed; explain it. Use numeric amounts only. Never repeat a bundled charge. Split a partially included item into its included portion and incremental cost in the notes.
5 · Resolve the comparison gates | Mark equivalent scope, commercial terms and all additional costs Confirmed only after review. Formula checks validate entries, not engineering or completeness of your contract.
6 · Use the summary carefully | Known amounts is a subtotal, not a final project price. Reviewed comparison total stays blank until all lines and gates are resolved. No automatic 'winner' is selected.
Input and formula key | Light-gray cells / blue text = input. Other cells = labels or formulas. Blank inputs are intentional. USD, CAD or another currency must be entered consistently; no currency conversion is performed.
What this is not | Not an engineering design, capacity calculation, permit approval, supplier quote or confirmation of stock/lead time. Have qualified parties verify compatibility, anchorage, site conditions and required approvals.
Review item | Quote A | Quote B | Quote C
Supplier
Quote reference
Currency
Readiness | INCOMPLETE — resolve inputs / scope | INCOMPLETE — resolve inputs / scope | INCOMPLETE — resolve inputs / scope
Quoted total
Known extra / by-others costs
Known amounts — NOT FINAL
Open scope / cost rows | 15 | 15 | 15
Reviewed comparison total
Across-quote check | Need at least two reviewed quotes
Keep a copy of the supplier's quote and written clarifications with this workbook. Do not overwrite formulas.
Pallet Rack Systems | https://mh-usa.com/pallet-rack/
Design | https://mh-usa.com/pallet-rack-design-services/
Pricing | https://mh-usa.com/pallet-rack/cost-pricing/
Installation | https://mh-usa.com/pallet-rack/installation/
Request a quote | https://mh-usa.com/request-a-quote/

## Project brief
Project brief ¦ Send the same revision to each supplier
Use TBD for unknowns. List multiple load types or phases separately in the answer or an attachment.
(800) 326-4403 | sales@mh-usa.com | mh-usa.com
Field | Your information | Prompt / unit to confirm
Project / company |  | Name this project without mixing phases.
Contact / preferred reply details |  | Share only the business contact details needed.
Revision / date |  | Update when loads, quantities or site requirements change.
Project type |  | New / add / replace / relocate.
Ship-to location |  | City, state, ZIP; confirm full address privately with supplier.
Target ready-to-use date |  | Separate shipment, delivery and installation dates. Confirm freight is fixed or estimated, its valid-through date and required change approval.
Loaded pallet width × depth × height |  | State units; include load overhang.
Maximum loaded pallet weight |  | State units; include pallet and load.
Other loads / handling requirements |  | Different dimensions, weight, pallets or picking needs.
Pallet positions required |  | State whether floor positions are included.
Levels above floor |  | Per bay; not the same as pallet-position count.
Bay / row counts and dimensions |  | If known; attach a dated sketch.
Upright frames: count / height / depth |  | Identify quantity units and part/model if known.
Beams: count / length / part |  | Explicitly say individual beams or pairs.
Decking / supports / accessories |  | Record quantities per level or total; identify which.
Existing rack identification / condition |  | Manufacturer, labels, connector photos; flag damaged/unknown parts.
Forklift make / model / capabilities |  | Operating aisle requirements, lift height and relevant truck data.
Usable area / clear height |  | Include doors, columns and overhead obstructions.
Building / slab / fire / permit review |  | List available records and who will confirm requirements.
Delivery / dock / unloading |  | Access restrictions, appointments and receiving equipment. Confirm applicability and owner of any waiting, redelivery or storage fees.
Installation / assembly |  | Confirm factory- vs. field-assembled parts and that current manufacturer hardware/instructions are supplied.
Site work hours / phases / traffic |  | Occupied work, clearance and sequencing restrictions.
Move / removal scope |  | Old and new sites; teardown, sorting, transport, reinstallation. Confirm bundle labels, counts, weights/dimensions and the loading/unloading owner at each site.
Floor restoration / disposal |  | Identify who handles old anchors, holes and disposal.
Drawings / photos / attachments |  | Record filenames, revision/date and anything not yet verified.
Other requirements / unresolved items |  | Record special constraints and who must confirm each.

## Quote A
Quote A ¦ Scope, costs and responsibilities
Start with the supplier's quoted total. Add only costs OUTSIDE that total. Gray cells are inputs.
(800) 326-4403 | sales@mh-usa.com |  | mh-usa.com
Supplier
Quote reference / revision
Currency (e.g. USD)
Quoted total
Quote date / valid through
Estimated ship / install dates
Equivalent project scope?
Commercial terms reviewed?
All additional costs covered?
Scope line | Status | Cost outside quoted total | Responsible party | Notes / quote reference
Rack frames and beams |  |  |  |  | 1
Decking and load supports |  |  |  |  | 1
Anchors, shims and hardware |  |  |  |  | 1
Guards, ties, labels and accessories |  |  |  |  | 1
Freight and packaging |  |  |  |  | 1
Receiving and unloading |  |  |  |  | 1
Rack installation labor |  |  |  |  | 1
Lifts, forklifts and site equipment |  |  |  |  | 1
Engineering and submittals |  |  |  |  | 1
Permit fees and application work |  |  |  |  | 1
Inspection and closeout |  |  |  |  | 1
Teardown, sorting and disposal |  |  |  |  | 1
Transport and reinstallation |  |  |  |  | 1
Floor repair and restoration |  |  |  |  | 1
Taxes and other charges |  |  |  |  | 1
Known extra / by-others costs
Known amounts — NOT FINAL
Open scope / cost rows | 15
Reviewed comparison total
Readiness | INCOMPLETE — resolve inputs / scope
Included / Not needed → no additional cost. Extra cost / By others → enter an amount, even if a verified zero. Unclear → unresolved. A numeric subtotal never proves complete scope.
Record responsibility and written evidence for each relevant line. If work is partially included, enter only its extra portion and explain the split. Use Follow-up for unresolved items.
Note on B8: Total as supplied, including every amount already in that total. Record tax treatment in scope notes. Additional amounts below must NOT already be in this number.
Note on B11: Same brief, loads, configuration, quantity units, condition, ship-to and services. Confirmed is not an engineering approval.
Note on B12: Review payment, warranty, exclusions, validity, dates and delivery assumptions. Record differences in follow-up.
Note on B13: Confirm all incremental expenses and by-others work, including taxes, allowances and extra scope, are captured without double counting.
Note on A16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on E16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on A17: List decks, crossbars, pallet supports and intended load support.
Note on E17: List decks, crossbars, pallet supports and intended load support.
Note on A18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on E18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on A19: Identify every accessory and who supplies it.
Note on E19: Identify every accessory and who supplies it.
Note on A20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on E20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on A21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on E21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on A22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on E22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on A23: Identify equipment, operator, rental duration and who provides each.
Note on E23: Identify equipment, operator, rental duration and who provides each.
Note on A24: Separate preliminary layouts from project-specific engineered documents.
Note on E24: Separate preliminary layouts from project-specific engineered documents.
Note on A25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on E25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on A26: Define required inspections, load labels and closeout documentation.
Note on E26: Define required inspections, load labels and closeout documentation.
Note on A27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on E27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on A28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on E28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on A29: Assign old anchors, hole repair and any building restoration.
Note on E29: Assign old anchors, hole repair and any building restoration.
Note on A30: Include applicable tax and every remaining charge or allowance.
Note on E30: Include applicable tax and every remaining charge or allowance.

## Quote B
Quote B ¦ Scope, costs and responsibilities
Start with the supplier's quoted total. Add only costs OUTSIDE that total. Gray cells are inputs.
(800) 326-4403 | sales@mh-usa.com |  | mh-usa.com
Supplier
Quote reference / revision
Currency (e.g. USD)
Quoted total
Quote date / valid through
Estimated ship / install dates
Equivalent project scope?
Commercial terms reviewed?
All additional costs covered?
Scope line | Status | Cost outside quoted total | Responsible party | Notes / quote reference
Rack frames and beams |  |  |  |  | 1
Decking and load supports |  |  |  |  | 1
Anchors, shims and hardware |  |  |  |  | 1
Guards, ties, labels and accessories |  |  |  |  | 1
Freight and packaging |  |  |  |  | 1
Receiving and unloading |  |  |  |  | 1
Rack installation labor |  |  |  |  | 1
Lifts, forklifts and site equipment |  |  |  |  | 1
Engineering and submittals |  |  |  |  | 1
Permit fees and application work |  |  |  |  | 1
Inspection and closeout |  |  |  |  | 1
Teardown, sorting and disposal |  |  |  |  | 1
Transport and reinstallation |  |  |  |  | 1
Floor repair and restoration |  |  |  |  | 1
Taxes and other charges |  |  |  |  | 1
Known extra / by-others costs
Known amounts — NOT FINAL
Open scope / cost rows | 15
Reviewed comparison total
Readiness | INCOMPLETE — resolve inputs / scope
Included / Not needed → no additional cost. Extra cost / By others → enter an amount, even if a verified zero. Unclear → unresolved. A numeric subtotal never proves complete scope.
Record responsibility and written evidence for each relevant line. If work is partially included, enter only its extra portion and explain the split. Use Follow-up for unresolved items.
Note on B8: Total as supplied, including every amount already in that total. Record tax treatment in scope notes. Additional amounts below must NOT already be in this number.
Note on B11: Same brief, loads, configuration, quantity units, condition, ship-to and services. Confirmed is not an engineering approval.
Note on B12: Review payment, warranty, exclusions, validity, dates and delivery assumptions. Record differences in follow-up.
Note on B13: Confirm all incremental expenses and by-others work, including taxes, allowances and extra scope, are captured without double counting.
Note on A16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on E16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on A17: List decks, crossbars, pallet supports and intended load support.
Note on E17: List decks, crossbars, pallet supports and intended load support.
Note on A18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on E18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on A19: Identify every accessory and who supplies it.
Note on E19: Identify every accessory and who supplies it.
Note on A20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on E20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on A21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on E21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on A22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on E22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on A23: Identify equipment, operator, rental duration and who provides each.
Note on E23: Identify equipment, operator, rental duration and who provides each.
Note on A24: Separate preliminary layouts from project-specific engineered documents.
Note on E24: Separate preliminary layouts from project-specific engineered documents.
Note on A25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on E25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on A26: Define required inspections, load labels and closeout documentation.
Note on E26: Define required inspections, load labels and closeout documentation.
Note on A27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on E27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on A28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on E28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on A29: Assign old anchors, hole repair and any building restoration.
Note on E29: Assign old anchors, hole repair and any building restoration.
Note on A30: Include applicable tax and every remaining charge or allowance.
Note on E30: Include applicable tax and every remaining charge or allowance.

## Quote C
Quote C ¦ Scope, costs and responsibilities
Start with the supplier's quoted total. Add only costs OUTSIDE that total. Gray cells are inputs.
(800) 326-4403 | sales@mh-usa.com |  | mh-usa.com
Supplier
Quote reference / revision
Currency (e.g. USD)
Quoted total
Quote date / valid through
Estimated ship / install dates
Equivalent project scope?
Commercial terms reviewed?
All additional costs covered?
Scope line | Status | Cost outside quoted total | Responsible party | Notes / quote reference
Rack frames and beams |  |  |  |  | 1
Decking and load supports |  |  |  |  | 1
Anchors, shims and hardware |  |  |  |  | 1
Guards, ties, labels and accessories |  |  |  |  | 1
Freight and packaging |  |  |  |  | 1
Receiving and unloading |  |  |  |  | 1
Rack installation labor |  |  |  |  | 1
Lifts, forklifts and site equipment |  |  |  |  | 1
Engineering and submittals |  |  |  |  | 1
Permit fees and application work |  |  |  |  | 1
Inspection and closeout |  |  |  |  | 1
Teardown, sorting and disposal |  |  |  |  | 1
Transport and reinstallation |  |  |  |  | 1
Floor repair and restoration |  |  |  |  | 1
Taxes and other charges |  |  |  |  | 1
Known extra / by-others costs
Known amounts — NOT FINAL
Open scope / cost rows | 15
Reviewed comparison total
Readiness | INCOMPLETE — resolve inputs / scope
Included / Not needed → no additional cost. Extra cost / By others → enter an amount, even if a verified zero. Unclear → unresolved. A numeric subtotal never proves complete scope.
Record responsibility and written evidence for each relevant line. If work is partially included, enter only its extra portion and explain the split. Use Follow-up for unresolved items.
Note on B8: Total as supplied, including every amount already in that total. Record tax treatment in scope notes. Additional amounts below must NOT already be in this number.
Note on B11: Same brief, loads, configuration, quantity units, condition, ship-to and services. Confirmed is not an engineering approval.
Note on B12: Review payment, warranty, exclusions, validity, dates and delivery assumptions. Record differences in follow-up.
Note on B13: Confirm all incremental expenses and by-others work, including taxes, allowances and extra scope, are captured without double counting.
Note on A16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on E16: Confirm manufacturer, part IDs, sizes, quantities and new/used condition.
Note on A17: List decks, crossbars, pallet supports and intended load support.
Note on E17: List decks, crossbars, pallet supports and intended load support.
Note on A18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on E18: Confirm specified hardware; no universal anchor or compatibility assumption.
Note on A19: Identify every accessory and who supplies it.
Note on E19: Identify every accessory and who supplies it.
Note on A20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on E20: Confirm ship-to, shipment count, packaging, freight allowances, whether the rate is fixed or estimated, its validity date and who approves a rate change before shipment.
Note on A21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on E21: Name the receiving party, dock/lift needs and appointment requirements. Confirm whether detention, failed-delivery/redelivery or storage charges could apply, what triggers each and who is responsible—per the actual carrier/quote terms, not a fixed time threshold.
Note on A22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on E22: Define assembly, anchoring, layout and included installation tasks. Note which parts arrive factory-assembled versus field-assembled, and confirm current manufacturer hardware/instructions are supplied for field work.
Note on A23: Identify equipment, operator, rental duration and who provides each.
Note on E23: Identify equipment, operator, rental duration and who provides each.
Note on A24: Separate preliminary layouts from project-specific engineered documents.
Note on E24: Separate preliminary layouts from project-specific engineered documents.
Note on A25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on E25: Confirm jurisdiction requirements, applicant, fees and review tasks.
Note on A26: Define required inspections, load labels and closeout documentation.
Note on E26: Define required inspections, load labels and closeout documentation.
Note on A27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on E27: If relocating/replacing, identify removal, sorting and disposal scope. For a relocation, confirm labelled bundles and component counts once teardown is complete.
Note on A28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on E28: If moving, include loading, transport and new-site installation review. Confirm actual weights/dimensions after teardown and who handles pickup/unloading handoff at the new site before freight is booked.
Note on A29: Assign old anchors, hole repair and any building restoration.
Note on E29: Assign old anchors, hole repair and any building restoration.
Note on A30: Include applicable tax and every remaining charge or allowance.
Note on E30: Include applicable tax and every remaining charge or allowance.

## Follow-up
Follow-up ¦ Resolve differences before selecting a quote
Log missing scope, unpriced work, drawing revisions, dates and commercial differences. Keep written answers.
(800) 326-4403 |  | sales@mh-usa.com | mh-usa.com
Quote | Topic | Question / written answer reference | Owner | Due date | Status